## Clause Library
Clause / Topic | Location | Plain English Meaning | Beneath the Lines | Who Holds Leverage | Notice / Time Bar | Money Impact | Schedule Impact | Practical Action / Evidence
Contract basics | Agreement / Contract Data | Project is the Big Project civil works between Roya as Employer and Samco as Contractor, effective 30-Apr-2025. | All later letters should be read against this baseline: parties, project, price, time, and risk allocation are fixed from this date. | Neutral | Use exact contract references in all notices. | Defines the starting commercial baseline. | Defines the baseline programme period. | Keep contract date, parties, amount, and commencement records in every claim file.
Accepted Contract Amount | Agreement / Appendix | Contract amount is EGP 367,286,025 including social insurance, duties, and taxes except VAT. | The price is intended to be comprehensive. The Contractor must prove why any extra is outside the agreed scope or qualifies under variation/adjustment clauses. | Employer | Any extra must follow Variation or Claim procedure. | High barrier to extra payment unless clear instruction/change exists. | No direct time right unless linked to variation or delay event. | For each extra cost, attach instruction, BOQ gap analysis, and timely notice.
Re-measured contract | Agreement / Appendix | Contract is on a re-measured basis and payment is based on actual executed quantities. | Quantities can increase or decrease, but rates and risk wording still matter. More quantity is not automatically a new scope claim. | Shared | Measurement records must be timely and supported. | Payment follows measured work, not tender BOQ quantity warranty. | Quantity change may affect time only if it impacts critical path and is claimed. | Keep survey sheets, IR approvals, measurement sheets, and BOQ mapping.
BOQ quantity no warranty | Agreement | Employer gives no warranty that BOQ quantities are accurate. | The Contractor cannot rely only on tender quantities to claim surprise. The claim must be tied to changed scope, instruction, or unforeseeable condition. | Employer | Claim notice still required if quantity change delays or costs more than normal remeasurement. | Limits quantity-based claims. | Possible only if actual quantity change affects critical path and is properly proved. | Compare tender BOQ, IFC drawings, actual measurements, and programme impact.
Fixed and final price wording | Appendix | Accepted amount is fixed and final, inclusive of compensation, contingencies, future law, fuel, and currency changes except specified material adjustment. | This is a strong anti-claim clause. Most market escalation arguments are blocked unless they fit the concrete/steel adjustment formula. | Employer | Use price adjustment clause only where allowed. | Reduces escalation and hardship claims. | No direct EOT from price movement. | Separate allowed concrete/steel adjustment from general inflation claims.
Concrete and steel price adjustment | Appendix | Concrete and steel may be adjusted using CAPMAS indices if delay is not due to Contractor. | Price adjustment is conditional. If Employer/Engineer says the Contractor caused the delay, the adjustment may be rejected. | Shared | Need proof delay was not Contractor-caused. | Potential recovery for concrete/steel escalation only. | Depends on non-contractor delay period and affected procurement. | Prepare CAPMAS index comparison, baseline prices, procurement dates, and delay responsibility analysis.
Exclusions from contract amount | Appendix | Employer/Engineer site mobilization, authority permits/licenses, relocation/protection of utilities, and dewatering are excluded. | These are possible entitlement areas, but only if actually instructed or required and not already covered elsewhere. | Contractor if documented | Variation/claim notice required before or immediately after impact. | Potential additional payment if outside scope and instructed/required. | Potential EOT if critical and not Contractor fault. | Record instruction, site condition, authority requirement, photographs, and cost/time impact.
Advance payment structure | Appendix / Clause 14.2 | Advance payment is 25 percent; 30 percent cash against bank check and 70 percent as steel supplied by Employer according to approved programme. | Steel supply is commercially tied to the advance. But entitlement depends on approved programme and proper requisitions. | Shared | Steel delay notices should be immediate and linked to approved programme dates. | Employer-supplied steel affects advance/payment accounting. | Late steel may support delay only if critical and properly requested. | Keep approved programme, steel requisitions, delivery notes, and impact analysis.
Monthly statements and material on site | Clause 14.3 / 14.5 | Monthly statements include executed work and 70 percent of approved delivered materials/plants. | Materials can improve cash flow, but only if approved, delivered, insured, and documented as required. | Shared | Submit complete monthly statement with supporting records. | Incomplete support delays payment certification. | Indirect risk if cash flow affects progress, but not automatic EOT. | Attach delivery notes, approvals, photos, ownership/insurance records, and BOQ allocation.
Minimum IPC threshold | Appendix | Minimum IPC amount is 70 percent of monthly cash flow. | Small or weak IPCs can be administratively rejected or deferred. Payment entitlement is linked to monthly cash flow planning. | Employer | Monthly IPC must meet threshold and be complete. | Can delay cash collection if IPC below threshold. | Indirect cash-flow pressure; not itself an EOT event. | Align monthly valuation with approved cash flow and explain any shortfall.
Payment period | Clause 14.7 | Employer pays amounts due within 45 days after Engineer receives a complete statement and supporting documents. | The 45 days likely starts only after a compliant submission, not after an incomplete invoice. | Employer until submission complete | Late payment arguments need proof of complete submission date. | Interest or delayed payment arguments depend on compliance. | Suspension rights require strict clause compliance. | Keep transmittal, Engineer receipt date, checklist of supporting documents, and payment certificate.
Social insurance condition | Agreement / Payment terms | Proof of social insurance payment is required before subsequent IPC release. | Even technically valid work may be held up if social insurance evidence is missing. | Employer | Submit before each affected IPC cycle. | Payment can be delayed despite completed work. | Indirect cash flow risk only. | Keep receipts, certificates, and IPC checklist.
Retention | Appendix / Clause 14 | Retention is 5 percent; first half released at Taking-Over Certificate and second half after Defects Notification Period. | Cash is locked until formal completion milestones, not just physical progress. | Employer | Taking-over and defect records must be clean. | Cash retention affects final recovery. | Open defects delay release. | Track TOC requirements, snag/NCR closure, and DNP expiry.
Performance security | Appendix / Clause 4.2 | Performance security is 5 percent of Accepted Contract Amount. | Security gives Employer leverage if termination, default, or recovery of damages becomes serious. | Employer | Maintain valid security until required release. | Potential call/deduction risk. | No direct schedule effect, but default pressure is high. | Track validity, expiry, amendments, and Employer notices.
Time for Completion | Appendix / Clause 8.2 | Time for Completion is 19 months from Commencement Date. | All delay analysis should measure impact against this contractual completion window. | Employer unless EOT proved | EOT claim required for any excusable delay. | Delay damages risk after expiry without EOT. | Critical path must be shown against 19-month baseline. | Maintain approved baseline programme and monthly updates.
8-month structural milestone | Appendix | Ground floor ceiling slab completion is required within 8 months from Commencement and is not a Taking-Over section. | This is a milestone obligation but does not give partial taking-over protection. Delay can still be used as performance evidence. | Employer | Notify delay to milestone if affected. | Potential damages/pressure depending on contract use. | High control milestone for early works. | Track milestone logic, progress photos, inspections, and causes of delay.
Delay damages | Appendix / Clause 8.7 | Delay damages are 1 percent of outstanding works per week or part week, capped at 10 percent of Contract Price. | Even part of a week counts. Employer can use this as strong pressure once completion is late without EOT. | Employer | EOT must be claimed before delay damages crystallize. | High exposure, capped at 10 percent. | Critical if no approved EOT. | Update EOT register and forecast exposure weekly.
Normal working hours | Appendix / Clause 6.5 | Normal hours are 6 days per week and 8 hours per day. | Acceleration beyond normal hours may not be paid unless instructed or caused by an Employer-risk event and properly claimed. | Employer | Acceleration claim needs instruction or recoverable delay event. | Overtime often Contractor cost unless entitlement proved. | Recovery plans may require more resources without extra payment if Contractor delay. | Record instructions, productivity assumptions, manpower, and cause of acceleration.
Document priority | Clause 1.5 | Contract documents are prioritized by the Agreement sequence. | If two documents conflict, priority decides. But the Contractor must still flag conflicts before execution. | Shared | Notify ambiguity before starting affected work. | May block extra payment if Contractor proceeds silently. | May block EOT if late clarification caused by Contractor silence. | Maintain discrepancy notices and Engineer responses.
More stringent requirement governs | Clause 1.5 | If Employer considers a more stringent requirement applicable, Contractor must comply. | The stricter interpretation can be imposed first, with entitlement only if Contractor preserves claim rights. | Employer | Notify and claim if stricter requirement changes cost/time. | Potential extra cost only if valid variation/claim survives. | Potential delay only if critical and noticed. | Issue reservation letter before execution, then submit variation proposal.
Missing or blank BOQ items | Clause 1.5 | Missing, unpriced, or blank BOQ items are deemed included in other BOQ rates/prices. | A BOQ silence is not enough to claim extra. Contractor must show the work is truly outside the Contract, not just missing from a rate. | Employer | Variation notice required for true extra scope. | Strongly limits payment for omitted rate items. | No direct EOT unless scope/instruction affects critical path. | Map work to drawings/specs and explain why it is not implied or included.
Works shown in any document | Clause 1.5 | Work shown in any contract document but not another is deemed included in Accepted Contract Amount. | One drawing/specification reference can be enough to make the work included. | Employer | Raise discrepancy before execution. | Extra payment difficult if item appears anywhere in contract docs. | EOT difficult unless delayed instruction/change occurs. | Search all contract documents before asserting missing scope.
Necessary and implied works | Clause 1.5 | Works necessary for stability, completion, safe operation, or proper execution are included even if not expressly detailed. | The contract captures hidden enabling works. Many support, temporary, coordination, and completion items may be treated as included. | Employer | Claim only if beyond normal implied works and instructed/changed. | Limits extras for temporary or enabling items. | May create sequencing burden on Contractor. | Record why the work is unusual, instructed, or outside normal construction practice.
Discrepancies and ambiguities | Clause 1.5 / 1.8 | Contractor must notify Engineer of ambiguity, discrepancy, or error before starting affected work. | If Contractor builds first and argues later, entitlement becomes weak. | Employer | Notify before work starts. | Late notice can defeat additional cost. | Late notice can defeat delay claim. | Send technical query/RFI with proposed interpretation and reservation of rights.
Contractor documents timing | Clause 1.8 | Submittals are due 14 days before construction activity; Engineer review is 10 days; resubmission is 3 days. | The programme must include approval cycles. Late submittals become Contractor delay even if Engineer takes normal review time. | Employer | Late submittal notices weaken claims. | Rework/resubmission cost likely Contractor risk. | Approval delay only claimable beyond contractual review if critical. | Maintain submittal register tied to programme activities.
Delayed drawings or instructions | Clause 1.9 | Delay from late drawings/instructions must be claimed under the notice procedure. | The event may be Employer-risk, but it is not automatically payable or excusable unless notice and particulars are on time. | Shared | Strict notice required, then particulars and monthly updates. | Potential cost/time only if claim compliant. | Potential EOT if critical path delayed. | Keep request dates, required-by dates, late response proof, and critical path analysis.
Site access | Clause 2.1 | Employer gives site access under contract conditions. | Access is entitlement-sensitive: if the Contractor cannot work because access is not given, it can be strong, but only with proof of readiness and criticality. | Contractor if ready | Immediate notice if access not available. | Possible cost if proven and not excluded. | Possible EOT if critical access denied. | Keep handover records, photographs, readiness evidence, and programme logic.
Permits and licenses | Clause 2.2 / Appendix exclusions | Authority permits/licenses are excluded from Accepted Contract Amount, but responsibilities depend on the specific permit and law. | This is a possible variation/claim zone, but not a blanket excuse for slow authority processing. | Shared | Notify authority delay and cost as soon as known. | Recoverable if Employer-risk or excluded cost instructed/required. | Possible EOT if authority issue blocks critical work and Contractor acted diligently. | Keep applications, authority receipts, correspondence, and delay chronology.
Engineer authority and determination | Clauses 3.1 / 3.5 | Engineer administers instructions and determinations under the Contract. | Engineer decisions are central evidence. Silence or informal site discussion is weaker than written instruction/determination. | Employer/Engineer | Ask for written instruction/determination where impact exists. | Payment depends on formal valuation/determination. | Delay depends on accepted programme impact. | Convert verbal directions into written confirmation immediately.
Contractor general obligations | Clause 4.1 | Contractor must execute, complete, and remedy defects in accordance with the Contract and good practice. | Broad duty means Contractor carries coordination, means, methods, and completion risk unless a clause shifts it. | Employer | Notify only where Employer-risk event prevents performance. | Defects/rework usually Contractor cost. | Contractor-caused delay not excusable. | Keep method statements, approvals, inspection records, and defect closure evidence.
Design verification and review | Clause 4.1 / General Requirements | Contractor must verify and review design documents as required by the Contract. | Failure to review early can make later design objections look like Contractor delay or late discovery. | Employer | Raise design issues promptly and before affected works. | Late design comments may not justify extra cost. | Late review can delay shop drawings/procurement. | Maintain design review log, consultant reports, RFIs, and dates.
Cooperation with others | Clause 4.6 / 20.1 | Contractor must cooperate with other contractors and anticipate simultaneous work. | Minor disruption, sequencing changes, and interface inconvenience may already be priced and programmed. | Employer | Only substantial, critical, Employer-caused interference should be claimed. | Minor interface cost likely unrecoverable. | Minor resequencing likely no EOT. | Keep interface meeting minutes, obstruction logs, photos, and critical path proof.
Unforeseeable physical conditions | Clause 4.12 / 20.1 | Unexpected physical conditions may support entitlement if properly notified and proven. | Site difficulty alone is not enough. Contractor must show unforeseeability, impact, and compliance with notice rules. | Shared | Immediate notice before disturbing evidence where possible. | Possible cost if conditions qualify. | Possible EOT if critical path affected. | Preserve photos, survey, test reports, expert opinion, and baseline assumptions.
Utilities and existing services | Clause 4.19 / Appendix exclusions | Utilities relocation/protection is excluded from price, but Contractor must manage site utilities obligations carefully. | Utility events can be claimable if outside scope, but damage or poor protection can become Contractor liability. | Shared | Notify conflict/damage immediately and follow variation/claim procedure. | Potential extra for instructed protection/relocation; liability if Contractor damages utilities. | Potential EOT if utility issue blocks critical work and not Contractor fault. | Keep utility drawings, trial pit records, permits, photos, and incident reports.
Employer equipment and free-issue materials | Clause 4.20 / Appendix | Employer-supplied items, especially steel as part of advance, depend on approved programme and requisition process. | A steel delay claim needs proof that Contractor requested correctly, was ready to use it, and the delay hit critical path. | Shared | Notice immediately if free issue material is late, defective, or short. | May affect payment/advance and possible prolongation. | Possible EOT if critical and not Contractor-caused. | Keep approved programme, requisitions, delivery notes, stock records, and activity impacts.
Progress reports | Clause 4.21 / General Requirements | Daily, weekly, and monthly reports must include progress, delay analysis, programme update, logs, photos, procurement, submittals, quality, and pending issues. | Reports are not paperwork only. They become the project record for delay, payment, and claim proof. | Employer if missing | Monthly claim/variation account must be separate and up to date. | Weak reports weaken IPCs and claims. | Weak reports weaken delay analysis. | Submit complete reports and reconcile them with notices, programme updates, and IPCs.
Shop drawings and as-builts | Clause 4.25 / General Requirements | Contractor must submit shop drawings, as-built drawings, and source files where required. | Late or incomplete drawings can stop approvals, inspections, and taking-over. | Employer | Follow submittal timing and resubmission period. | Rework/correction generally Contractor cost. | Can become Contractor delay if on critical path. | Maintain drawing register, revision history, approvals, and transmittals.
Quality assurance system | Clause 4.26 / General Requirements | If Contractor fails to submit or obtain approval of QMS, Employer/RFP quality plan may be deemed final. | Contractor loses control over the quality framework if its own plan is late or rejected. | Employer | QMS details due early after commencement. | Noncompliance can lead to rejected work and withheld approvals. | Rejected IRs/NCRs can delay progress and taking-over. | Submit QMS, QC manager approval, ITPs, NCR logs, and corrective action records.
HSE system | Clause 6.7 / General Requirements | If Contractor fails to submit or approve HSE plan, Employer/RFP safety plan may govern. | Safety noncompliance can stop work and still remain Contractor risk. | Employer | Submit HSE plan and incident reports on time. | Stop-work or corrective measures may be Contractor cost. | Safety stoppages can delay works without EOT if Contractor fault. | Keep HSE plan, inductions, toolbox talks, PPE logs, accident reports, and close-outs.
Personnel approval | Clause 6.9 | Key Contractor personnel require approval and compliance with contract requirements. | Changing or lacking approved staff can be treated as management noncompliance and used against progress claims. | Employer | Notify changes and obtain approvals. | May affect payment/certification indirectly. | Weak staffing undermines EOT defenses. | Keep CV approvals, org chart, attendance, and replacement approvals.
Programme requirements | Clause 8.3 / General Requirements | Programme must be P6, resource/cost/cash loaded, with narratives, long lead items, free issue materials, and other contractors' milestones. | A simple bar chart is not enough. Without a compliant baseline/update, delay claims become much harder to prove. | Employer | Programme submission and monthly update deadlines matter. | IPC, cash flow, and delay claims depend on programme quality. | Critical path proof depends on accepted logic. | Keep baseline, updates, narratives, calendars, resources, cash flow, and change logs.
Recovery plan trigger | General Requirements / Clause 8.6 | If delay reaches 10 percent of remaining calendar days or at least 45 days, Contractor must submit recovery plan within 28 days. | The contract creates an early warning and acceleration pressure mechanism before final delay damages. | Employer | Recovery plan due within 28 days after update showing delay. | Recovery may be Contractor cost if delay is Contractor risk. | Failure worsens delay exposure. | Submit recovery plan with manpower, shifts, resequencing, procurement, and float recovery.
Extension of time | Clause 8.4 / 20.1 | EOT is available only for qualifying events and compliant claims. | Even a real Employer-caused delay can be lost if notice, particulars, monthly updates, or critical path proof are missing. | Shared | Strict claim notice and monthly account requirements. | Prolongation cost depends on entitlement and concurrency rules. | EOT protects against delay damages if proven. | Maintain delay event register, notices, particulars, updates, and delay analysis.
Rate of progress | Clause 8.6 | If progress is too slow, Contractor may be required to revise methods or accelerate. | If the delay is Contractor-caused, recovery is usually at Contractor cost. | Employer | Respond quickly to slow-progress notices. | Additional resources may not be payable. | Recovery obligations can change sequence and productivity. | Keep productivity records and separate Contractor delay from Employer delay.
Suspension by Employer | Clause 8.11 | Engineer/Employer may instruct suspension under contract conditions. | Suspension can be entitlement-bearing if not Contractor fault, but must be documented precisely. | Shared | Notice/claim immediately after suspension instruction and resumption. | Possible cost if compensable under contract. | Possible EOT if critical path affected. | Keep suspension instruction, affected resources, idle plant/labour, and restart records.
Tests on completion and failed tests | Clause 9.4 | Failure to pass tests can trigger remedial obligations and retesting. | Testing failure usually shifts time/cost risk back to Contractor unless caused by Employer design/instruction. | Employer | Notify cause if failure not Contractor fault. | Retesting/remedial cost likely Contractor risk. | Failed tests delay taking-over. | Keep test plans, results, calibration, causes, corrective works, and retest approvals.
Taking-over requirements | Clause 10 / General Requirements | Taking-over requires substantial completion and conditions such as no rejected IRs, no open NCRs, clear site limits, debris removal, and safe access. | Physical completion is not enough. Paperwork, NCRs, housekeeping, and safe access can block TOC and retention release. | Employer | Apply for TOC only with supporting close-out evidence. | Retention release and final payment depend on TOC. | Delay damages risk continues until TOC/completion accepted. | Prepare TOC dossier, NCR closeout, as-builts, test certificates, and site clearance evidence.
Defects Notification Period | Clause 11 | DNP is 365 days and Contractor must remedy defects. | The project is not commercially finished at TOC. Defects affect final retention and final certificate. | Employer | Respond to defect notices promptly. | Unremedied defects may be deducted or completed by others. | Defects can delay final release. | Maintain defect register, response dates, repair records, and Engineer acceptance.
Measurement and evaluation | Clause 12 | Works are measured and evaluated under contract rules. | Approved inspection is not always approved payment quantity. Measurement evidence must match BOQ rules. | Shared | Submit measurements promptly and resolve disagreements. | Direct basis for IPC and final account. | Quantity disputes can delay certification. | Keep joint measurements, sketches, survey data, and signed quantity sheets.
Right to vary | Clause 13.1 | Employer/Engineer may instruct variations within the contractual mechanism. | Contractor generally must proceed with instructed variation and argue valuation/time through the procedure, not refuse execution. | Employer | Reservation and proposal must follow Clause 13.3/20.1. | Potential payment if instructed and valued. | Possible EOT if variation delays critical path. | Get written instruction, submit proposal, maintain records, and update programme.
Variation procedure | Clause 13.3 | Variations require notice/proposal procedure, including time and cost impact. | A variation without a timely proposal and monthly claim account may become hard to recover later. | Shared | Very important: submit notice/proposal within required period and include monthly account. | Preserves extra payment. | Preserves EOT if critical. | Use a variation register with instruction date, notice date, proposal date, status, and monthly update.
Batching plant duties | General Requirements | Contractor duties under Employer-ready mix supplier/batch plant arrangement are treated as Variation under Clause 13. | This is a useful entitlement hook: if duties arise from Employer's batching plant arrangement, process them as variation, not informal cooperation. | Contractor if documented | Clause 13 notice/proposal required. | Potential extra payment. | Possible time if duties affect critical path. | Record instruction, duties performed, resources, location impacts, and cost/time proposal.
Tax and VAT | Agreement / Clause 14.16 / 14.17 | Accepted amount excludes VAT but includes other duties/taxes as stated. | Do not mix VAT entitlement with general tax escalation. VAT treatment must follow invoicing and law. | Shared | Tax documents must support IPC/final account. | VAT may be separate; other taxes likely included. | No direct schedule effect. | Keep tax invoices, VAT calculations, withholding records, and contract tax basis.
Termination by Employer | Clause 15.2 / 15.5 | Employer has termination rights for serious Contractor default and may recover consequences. | Repeated noncompliance, delay, missing security/insurance, or abandonment can escalate beyond letters into termination risk. | Employer | Default notices and cure periods must be tracked. | High financial exposure including security and completion costs. | Works may be removed from Contractor. | Maintain compliance matrix and respond formally to all default notices.
Contractor suspension or termination | Clause 16 | Contractor may suspend or terminate only under strict contractual grounds. | Suspending work without satisfying clause conditions can backfire as Contractor default. | Employer unless strict compliance | Strict notices required before suspension/termination. | Potential protection if Employer seriously fails payment/obligation. | Improper suspension creates delay damages risk. | Before stopping work, verify notices, due dates, unpaid certified amounts, and legal advice.
Indemnities | Clause 17.1 | Parties indemnify against defined losses, but Contractor carries broad responsibility for works, personnel, and damage caused by its operations. | Damage events should be managed as liability matters, not only construction issues. | Employer for Contractor-caused damage | Notify incidents immediately. | Potential uninsured or deductibles exposure. | Repairs can delay works without EOT if Contractor fault. | Keep incident reports, photos, witness statements, insurance notices, and repair records.
Insurance | Clause 18.1 | Contractor must provide evidence before start, policies within 28 days, maintain cover, include Employer protections, and use approved insurers. | No insurance equals major noncompliance. Employer may insure and deduct, and uninsured losses can stay with Contractor. | Employer | Evidence before start; policies within 28 days of commencement. | High uninsured/deduction risk. | Equipment/site access may be restricted. | Keep policy schedule, endorsements, renewal proof, premium receipts, and Employer approval.
Force majeure | Clause 19.1 / 19.4 | Force majeure is narrowly defined and its consequence is EOT only because cost recovery is deleted. | Even a true force majeure event may not produce money. It mainly protects against delay damages through EOT. | Employer on cost, Contractor on time if proven | Notice required under force majeure and claim clauses. | No cost recovery under amended clause. | Possible EOT only. | Keep event evidence, impossibility/impact records, mitigation, and critical path delay analysis.
Claims time bar | Clause 20.1 | Failure to comply with claim notice requirements is an irrevocable waiver and release of Employer/Engineer from claims. | This is one of the strongest clauses. A good claim can die if the notice procedure is missed. | Employer | Strict notice, particulars, and monthly claim account. | Missed notice can erase payment claim. | Missed notice can erase EOT claim. | Maintain a live claims register and send protective notices early.
Monthly claim and variation account | Clause 20.1 | Contractor must submit a separate monthly account of all claims and variations; claims not included may not be considered. | A notice alone is not enough. Every month, live claims must be repeated and updated. | Employer | Monthly account required for all claims/variations. | Omitted items risk being rejected later. | Omitted delay events risk weaker EOT. | Use monthly claim account with status, amount, time, evidence, and updated particulars.
Concurrent delay rule | Clause 20.1 | For concurrent delays, Contractor may get EOT but no cost for the concurrent period if compliant. | This protects against delay damages but blocks prolongation cost where Contractor and Employer delays overlap. | Employer on money, Contractor on time | Notice still required. | No cost during concurrent period. | Possible EOT only. | Delay analysis must separate Employer delay, Contractor delay, and concurrent periods.
Engineer decision before dispute | Clause 20.2 | Disputes first go to Engineer, who decides within 42 days; parties must comply unless revised later. | The Engineer decision is the gate before final dispute. Missing the dissatisfaction deadline can make it final. | Employer/Engineer | Notice of dissatisfaction within 28 days if disagreeing. | Decision affects valuation/payment rights. | Decision affects EOT/delay damages position. | Track referral date, decision due date, decision date, and dissatisfaction deadline.
No DAB and court route | Clauses 20.3 to 20.8 | DAB and arbitration are deleted; disputes proceed through Engineer decision, amicable/mediation route, then court. | Disputes may be slower and more document-heavy. Project records become even more important. | Neutral | Follow Engineer decision and dissatisfaction steps before court. | Recovery may take longer. | Dispute process does not excuse slow progress unless contract allows. | Preserve full contemporaneous records and avoid relying on informal promises.
Prequalification of steel suppliers | General Requirements | At least 3 reinforcement steel suppliers must be prequalified one month before procurement per programme. | Steel delay cannot be blamed only on market supply if supplier prequalification was late or weak. | Employer | Submit supplier prequalification before procurement date. | Late supplier approval can delay payment/procurement. | Can become Contractor delay to reinforcement works. | Keep supplier list, submissions, approvals, procurement dates, and delivery commitments.
Prequalification of concrete suppliers | General Requirements | At least 5 concrete suppliers and 3 backup ready-mix factories must be prequalified one month before procurement. | The Contractor must have backup supply capacity. Concrete supply failure may be treated as Contractor planning risk. | Employer | Submit prequalification before procurement date. | Extra cost for alternative supply may be Contractor risk. | Concrete shortage can delay structure without EOT if Contractor fault. | Keep supplier approvals, plant capacity, backup arrangements, and delivery records.
Revit and CAD deliverables | General Requirements | Structural modeling must use Revit source files; other engineering is AutoCAD ASD unless stated. | Deliverable format is a contract requirement, not a preference. Wrong format can delay approvals and close-out. | Employer | Submit in required format and revision controls. | Rework of deliverables likely Contractor cost. | Wrong format can delay design review/as-builts/TOC. | Maintain source files, model issue log, drawing register, and transmittals.