## Contract Clause Library
Clause / Topic | Location | Plain English Meaning | Beneath the Lines | Who Holds Leverage | Notice / Time Bar | Money Impact | Schedule Impact | Practical Action / Evidence | Source File | Claim Type | Risk Level | Claim Strength | Exact Clause Text
Agreement Summary | 1 | This clause falls under Contractor Counterarguments. In practical contractor terms, it means: 1. Agreement Summary This synthetic contract record is prepared for the Suez-Tunnel Project comprising civil, structural, temporary works, tunnel approach structures, and associated utilities. The Employer is Suez Infrastructure Authority, the Contractor is SAMCO Egypt, and the Engineer / PMO is Suez PMO Consultant. Th | Tie the facts directly to the contractual exception or saving wording. | Shared | Unclear | Possible | Yes | Exception facts, supporting letters, notices, approvals, and event records. | Overall Contract.pdf | Counterargument / Exception | Medium | Medium | 1. Agreement Summary This synthetic contract record is prepared for the Suez-Tunnel Project comprising civil, structural, temporary works, tunnel approach structures, and associated utilities. The Employer is Suez Infrastructure Authority, the Contractor is SAMCO Egypt, and the Engineer / PMO is Suez PMO Consultant. The Agreement Effective Date is 15-Jan-2026 and the Commencement Date is 01-Feb-2026. Item Value Project Suez-Tunnel Project Contract Number ST-CTR-2026-001 Scope civil, structural, temporary works, tunnel approach structures, and associated utilities Accepted Contract Amount EGP 685,750,000 excluding VAT unless otherwise stated Time for Completion
months from the Commencement Date | 24 | This clause falls under Notice Requirements. In practical contractor terms, it means: 24 months from the Commencement Date Key Section Milestone first tunnel approach concrete and ground interface works within 9 months from Commencement Governing Law Laws of the Arab Republic of Egypt Ruling Language English | Demonstrate timely notice, continuing notice trail, or waiver / actual knowledge by the receiving party. | Shared | Unclear | Possible | Possible | Notice letters, emails, meeting minutes, proof of submission and receipt. | Overall Contract.pdf | Notice Compliance | Medium | Medium | 24 months from the Commencement Date Key Section Milestone first tunnel approach concrete and ground interface works within 9 months from Commencement Governing Law Laws of the Arab Republic of Egypt Ruling Language English
Document Priority | 2 | This clause falls under Risk Clauses. In practical contractor terms, it means: 2. Document Priority | Tie the clause wording to the factual event with contemporaneous evidence. | Shared | Unclear | Possible | Possible | Full clause context, event chronology, and project records. | Overall Contract.pdf | General Contract Risk | Low | Weak | 2. Document Priority
This Agreement | 1 | This clause falls under Risk Clauses. In practical contractor terms, it means: 1. This Agreement | Tie the clause wording to the factual event with contemporaneous evidence. | Shared | Unclear | Possible | Possible | Full clause context, event chronology, and project records. | Overall Contract.pdf | General Contract Risk | Low | Weak | 1. This Agreement
Appendix to Tender / Contract Data | 2 | This clause falls under Risk Clauses. In practical contractor terms, it means: 2. Appendix to Tender / Contract Data | Tie the clause wording to the factual event with contemporaneous evidence. | Shared | Unclear | Possible | Possible | Full clause context, event chronology, and project records. | Overall Contract.pdf | General Contract Risk | Low | Weak | 2. Appendix to Tender / Contract Data
Particular Conditions | 3 | This clause falls under Risk Clauses. In practical contractor terms, it means: 3. Particular Conditions | Tie the clause wording to the factual event with contemporaneous evidence. | Shared | Unclear | Possible | Possible | Full clause context, event chronology, and project records. | Overall Contract.pdf | General Contract Risk | Low | Weak | 3. Particular Conditions
General Conditions | 4 | This clause falls under Risk Clauses. In practical contractor terms, it means: 4. General Conditions | Tie the clause wording to the factual event with contemporaneous evidence. | Shared | Unclear | Possible | Possible | Full clause context, event chronology, and project records. | Overall Contract.pdf | General Contract Risk | Low | Weak | 4. General Conditions
General Requirements | 5 | This clause falls under Risk Clauses. In practical contractor terms, it means: 5. General Requirements | Tie the clause wording to the factual event with contemporaneous evidence. | Shared | Unclear | Possible | Possible | Full clause context, event chronology, and project records. | Overall Contract.pdf | General Contract Risk | Low | Weak | 5. General Requirements
Bill of Quantities | 6 | This clause falls under Risk Clauses. In practical contractor terms, it means: 6. Bill of Quantities | Tie the clause wording to the factual event with contemporaneous evidence. | Shared | Unclear | Possible | Possible | Full clause context, event chronology, and project records. | Overall Contract.pdf | General Contract Risk | Low | Weak | 6. Bill of Quantities
Drawings | 7 | This clause falls under Risk Clauses. In practical contractor terms, it means: 7. Drawings | Tie the clause wording to the factual event with contemporaneous evidence. | Shared | Unclear | Possible | Possible | Full clause context, event chronology, and project records. | Overall Contract.pdf | General Contract Risk | Low | Weak | 7. Drawings
Soil report, permits matrix, and site layout | 8 | This clause falls under Risk Clauses. In practical contractor terms, it means: 8. Soil report, permits matrix, and site layout | Tie the clause wording to the factual event with contemporaneous evidence. | Shared | Unclear | Possible | Possible | Full clause context, event chronology, and project records. | Overall Contract.pdf | General Contract Risk | Low | Weak | 8. Soil report, permits matrix, and site layout
Commercial Data | 3 | This clause falls under Payment Entitlements. In practical contractor terms, it means: 3. Commercial Data Commercial Topic Synthetic Contract Position Advance Payment | Show the certified / due amounts, delayed release, and the resulting impact on progress or cost. | Contractor | Unclear | Yes | Possible | Payment certificate, invoice, valuation, payment status records, and resulting disruption evidence. | Overall Contract.pdf | Payment / Certification | Medium | Strong | 3. Commercial Data Commercial Topic Synthetic Contract Position Advance Payment
% structured as 40% cash advance and 60% Employer-supplied steel/material | 20 | This clause falls under Risk Clauses. In practical contractor terms, it means: 20% structured as 40% cash advance and 60% Employer-supplied steel/material support according to the approved programme. Retention | Tie the clause wording to the factual event with contemporaneous evidence. | Shared | Unclear | Possible | Possible | Full clause context, event chronology, and project records. | Overall Contract.pdf | General Contract Risk | Low | Weak | 20% structured as 40% cash advance and 60% Employer-supplied steel/material support according to the approved programme. Retention
% of the Contract Price. | 5 | This clause falls under Risk Clauses. In practical contractor terms, it means: 5% of the Contract Price. Performance Security | Tie the clause wording to the factual event with contemporaneous evidence. | Shared | Unclear | Yes | Possible | Full clause context, event chronology, and project records. | Overall Contract.pdf | General Contract Risk | Low | Weak | 5% of the Contract Price. Performance Security
% of the Accepted Contract Amount unless waived by contract amendment. | 5 | This clause falls under Contractor Counterarguments. In practical contractor terms, it means: 5% of the Accepted Contract Amount unless waived by contract amendment. Minimum IPC | Tie the facts directly to the contractual exception or saving wording. | Shared | Unclear | Possible | Possible | Exception facts, supporting letters, notices, approvals, and event records. | Overall Contract.pdf | Counterargument / Exception | Medium | Medium | 5% of the Accepted Contract Amount unless waived by contract amendment. Minimum IPC
% of monthly cash flow | 65 | This clause falls under Payment Entitlements. In practical contractor terms, it means: 65% of monthly cash flow Payment Period | Show the certified / due amounts, delayed release, and the resulting impact on progress or cost. | Contractor | Unclear | Yes | Possible | Payment certificate, invoice, valuation, payment status records, and resulting disruption evidence. | Overall Contract.pdf | Payment / Certification | Medium | Strong | 65% of monthly cash flow Payment Period
days after Engineer receives the complete monthly statement | 45 | This clause falls under Payment Entitlements. In practical contractor terms, it means: 45 days after Engineer receives the complete monthly statement Delay Damages | Show the certified / due amounts, delayed release, and the resulting impact on progress or cost. | Shared | Unclear | Yes | Yes | Payment certificate, invoice, valuation, payment status records, and resulting disruption evidence. | Overall Contract.pdf | Payment / Certification | Critical | Medium | 45 days after Engineer receives the complete monthly statement Delay Damages
% of outstanding works per week of delay or part thereof, capped at 10% of | 0.75 | This clause falls under Evidence Requirements. In practical contractor terms, it means: 0.75% of outstanding works per week of delay or part thereof, capped at 10% of the Contract Price Material Adjustment Adjustment may apply only for approved material categories such as reinforcement steel, concrete additives, waterproofing materials, and embedded plates where delay is not Contractor-caused and evidence | Show that the required records exist and directly support the claimed event and impact. | Shared | Unclear | Yes | Yes | All records explicitly required by the clause plus supporting schedule and commercial evidence. | Overall Contract.pdf | Evidence / Substantiation | Medium | Strong | 0.75% of outstanding works per week of delay or part thereof, capped at 10% of the Contract Price Material Adjustment Adjustment may apply only for approved material categories such as reinforcement steel, concrete additives, waterproofing materials, and embedded plates where delay is not Contractor-caused and evidence is complete. ST-CTR-2026-001 ¦ Suez-Tunnel Project Page 3
Programme, Progress, and Delay Entitlement | 4 | This clause falls under EOT Entitlements. In practical contractor terms, it means: 4. Programme, Progress, and Delay Entitlement Programme Requirements. The Contractor shall submit and maintain a Primavera P6 baseline programme, monthly updates, narrative reports, cash flow, procurement curves, and recovery programmes where required. Extension of Time. EOT entitlement must demonstrate a delay on the | Support the claim with TIA / window logic, path analysis, and event-specific schedule evidence. | Contractor | Yes | Yes | Yes | Accepted programme basis, event window, contemporaneous records, CPM logic, notices. | Overall Contract.pdf | Extension of Time | High | Strong | 4. Programme, Progress, and Delay Entitlement Programme Requirements. The Contractor shall submit and maintain a Primavera P6 baseline programme, monthly updates, narrative reports, cash flow, procurement curves, and recovery programmes where required. Extension of Time. EOT entitlement must demonstrate a delay on the critical path using Time Impact Analysis, Windows Analysis, or another Engineer-approved method, supported by notices and contemporaneous records. Rate of Progress. If progress is slow against the approved programme, the Engineer may request a recovery programme. The Contractor must demonstrate mitigation, resequencing, and resource recovery measures. Concurrent Delay. Events must be split by responsibility, timing, affected activities, float, criticality, and actual schedule impact. Cost recovery may be reduced where Contractor concurrent delay exists. Notices and Claims. Delay, disruption, variation, and payment claims must be notified within the contractual period and fully substantiated by records, correspondence, measurement sheets, and cause-effect analysis.
Site, Materials, Quality, and HSE | 5 | This clause falls under Payment Entitlements. In practical contractor terms, it means: 5. Site, Materials, Quality, and HSE Site access and possession must permit practical execution of the Suez-Tunnel Project scope. Constraints relating to traffic diversions, dewatering interfaces, and utility protection must be recorded with dates, photographs, obstruction logs, and daily reports. Employer free-issue/m | Show the certified / due amounts, delayed release, and the resulting impact on progress or cost. | Shared | Unclear | Possible | Possible | Payment certificate, invoice, valuation, payment status records, and resulting disruption evidence. | Overall Contract.pdf | Payment / Certification | High | Medium | 5. Site, Materials, Quality, and HSE Site access and possession must permit practical execution of the Suez-Tunnel Project scope. Constraints relating to traffic diversions, dewatering interfaces, and utility protection must be recorded with dates, photographs, obstruction logs, and daily reports. Employer free-issue/material support is limited to approved items and must be requested against the approved programme. Shortage, late delivery, or defect records must be supported by requisitions, delivery notes, inspection records, and consumption logs. The Contractor shall maintain QA/QC procedures, inspection records, method statements, material approvals, as-built records, and source files in the contractually required formats. The Contractor shall implement HSE controls, permit-to-work processes, induction logs, incident records, corrective actions, and risk assessments suitable for the project interfaces.
Clause Intelligence Extract | 6 | This clause falls under Evidence Requirements. In practical contractor terms, it means: 6. Clause Intelligence Extract Clause / Topic Meaning Evidence Action Contract basics Project is the Suez-Tunnel Project civil, structural, temporary works, tunnel approach structures, and associated utilities between Suez Infrastructure Authority as Employer and SAMCO Egypt as Contractor, effective | Show that the required records exist and directly support the claimed event and impact. | Shared | Unclear | Possible | Possible | All records explicitly required by the clause plus supporting schedule and commercial evidence. | Overall Contract.pdf | Evidence / Substantiation | Medium | Medium | 6. Clause Intelligence Extract Clause / Topic Meaning Evidence Action Contract basics Project is the Suez-Tunnel Project civil, structural, temporary works, tunnel approach structures, and associated utilities between Suez Infrastructure Authority as Employer and SAMCO Egypt as Contractor, effective
Jan-2026. | 15 | This clause falls under Evidence Requirements. In practical contractor terms, it means: 15-Jan-2026. Keep contract date, commencement record, project access evidence, amount, parties, and baseline programme in every claim file. Accepted Contract Amount Contract amount is EGP 685,750,000 including social insurance, duties, and taxes except VAT. For each extra cost, attach Engineer instruction, BOQ gap anal | Show that the required records exist and directly support the claimed event and impact. | Contractor | Yes | Yes | Yes | All records explicitly required by the clause plus supporting schedule and commercial evidence. | Overall Contract.pdf | Evidence / Substantiation | High | Strong | 15-Jan-2026. Keep contract date, commencement record, project access evidence, amount, parties, and baseline programme in every claim file. Accepted Contract Amount Contract amount is EGP 685,750,000 including social insurance, duties, and taxes except VAT. For each extra cost, attach Engineer instruction, BOQ gap analysis, cost build-up, and timely notice. Advance payment structure Advance payment is 20%; structured as 40% cash advance and 60% Employer-supplied steel/material support according to the approved programme. Keep approved programme, material requisitions, delivery notes, bank guarantee records, and impact analysis. Time for Completion Time for Completion is 24 months from the Commencement Date. Maintain baseline, monthly updates, contemporaneous progress records, and approved recovery plans.
month structural | 8 | This clause falls under Delay Damages Defense. In practical contractor terms, it means: 8-month structural milestone Section milestone: first tunnel approach concrete and ground interface works within 9 months from Commencement. Track milestone fragnet, procurement constraints, concrete/steel delivery, and inspection readiness. Delay damages Delay damages are 0.75% of outstanding works per week of delay o | Use excusable delay and concurrency analysis to defeat or reduce liquidated damages exposure. | Shared | Unclear | Yes | Yes | Criticality analysis, entitlement basis, excusable delay record, concurrency review. | Overall Contract.pdf | Delay Damages Defense | Critical | Medium | 8-month structural milestone Section milestone: first tunnel approach concrete and ground interface works within 9 months from Commencement. Track milestone fragnet, procurement constraints, concrete/steel delivery, and inspection readiness. Delay damages Delay damages are 0.75% of outstanding works per week of delay or part thereof, capped at
% of the Contract Price. | 10 | This clause falls under Evidence Requirements. In practical contractor terms, it means: 10% of the Contract Price. Protect with timely notices, critical-path delay analysis, mitigation records, and cause-effect evidence. Employer equipment and free-issue materials Employer free-issue/material support covers approved items including reinforcement steel, concrete additives, waterproofing materials, and embe | Show that the required records exist and directly support the claimed event and impact. | Contractor | Yes | Yes | Yes | All records explicitly required by the clause plus supporting schedule and commercial evidence. | Overall Contract.pdf | Evidence / Substantiation | Critical | Strong | 10% of the Contract Price. Protect with timely notices, critical-path delay analysis, mitigation records, and cause-effect evidence. Employer equipment and free-issue materials Employer free-issue/material support covers approved items including reinforcement steel, concrete additives, waterproofing materials, and embedded plates where stated in the approved programme. Keep requisitions, delivery notes, inspection records, storage records, consumption logs, and fragnet analysis. ST-CTR-2026-001 ¦ Suez-Tunnel Project Page 4 Clause / Topic Meaning Evidence Action Extension of time EOT requires a delay demonstrated on the critical path using Time Impact, Windows Analysis, or another approved method. Prepare notice, event chronology, contemporaneous records, fragnet/window analysis, and mitigation evidence. Claims time bar Claims must be notified and supported within the contract time limits. Maintain notice register, claim register, event logs, correspondence, and full substantiation file. ST-CTR-2026-001 ¦ Suez-Tunnel Project Page 5
Execution Control Matrix | 7 | This clause falls under Payment Entitlements. In practical contractor terms, it means: 7. Execution Control Matrix Control Area Required Evidence Dashboard Usage Contract Baseline Agreement data, contract amount, scope, commencement, baseline programme Feeds project metadata, contract risk profile, and executive dashboard baseline. Payment IPC submissions, measurement sheets, material-on-site records, En | Show the certified / due amounts, delayed release, and the resulting impact on progress or cost. | Contractor | Yes | Yes | Yes | Payment certificate, invoice, valuation, payment status records, and resulting disruption evidence. | Overall Contract.pdf | Payment / Certification | High | Strong | 7. Execution Control Matrix Control Area Required Evidence Dashboard Usage Contract Baseline Agreement data, contract amount, scope, commencement, baseline programme Feeds project metadata, contract risk profile, and executive dashboard baseline. Payment IPC submissions, measurement sheets, material-on-site records, Engineer certification Feeds payment status, cash-flow risk, and commercial KPIs. Delay / EOT Notices, delay events, P6 updates, fragnet/window analysis, daily reports Feeds TIA engine, EOT potential, critical-path alerts, and claim strength score. Materials Requisitions, delivery notes, shortage logs, inspection records, consumption log Feeds steel/material delay exposure, supply-demand gap, and affected activities. Quality / HSE IRs, NCRs, method statements, safety permits, incident logs Feeds risk register, readiness score, compliance alerts, and management action list.
Signature Placeholders | 8 | This clause falls under Risk Clauses. In practical contractor terms, it means: 8. Signature Placeholders On behalf of the Employer On behalf of the Contractor Engineer / PMO Acknowledgement Company: Suez Infrastructure Authority Name: ___________________ Title: ___________________ Date: ___________________ Signature: ___________________ Company: SAMCO Egypt Name: ___________________ Title: ______ | Tie the clause wording to the factual event with contemporaneous evidence. | Shared | Unclear | Possible | Possible | Full clause context, event chronology, and project records. | Overall Contract.pdf | General Contract Risk | Low | Weak | 8. Signature Placeholders On behalf of the Employer On behalf of the Contractor Engineer / PMO Acknowledgement Company: Suez Infrastructure Authority Name: ___________________ Title: ___________________ Date: ___________________ Signature: ___________________ Company: SAMCO Egypt Name: ___________________ Title: ___________________ Date: ___________________ Signature: ___________________ Entity: Suez PMO Consultant Name: ___________________ Title: ___________________ Date: ___________________ Signature: ___________________ This file is synthetic and intended for testing project-control dashboards, clause extraction, and contract-intelligence workflows. It should not be used as a binding contract or relied on as legal advice.